## ProjectSchedule
CONTRACT PLAYBOOK COMPARISON SYSTEM | [6 empty] | ► Watch How to Make a Gantt Chart in Excel
SE Lab Project |  | Project Start: | 2026-08-03
[Project Lead] |  | Today: | 2026-09-13
|  | Display Week: | 1 |  |  | Week 1 ¦ 03 Aug – 09 Aug | [6 empty] | Week 2 ¦ 10 Aug – 16 Aug | [6 empty] | Week 3 ¦ 17 Aug – 23 Aug | [6 empty] | Week 4 ¦ 24 Aug – 30 Aug | [6 empty] | Week 5 ¦ 31 Aug – 06 Sep | [6 empty] | Week 6 ¦ 07 Sep – 13 Sep | [6 empty] | Week 7 ¦ 14 Sep – 20 Sep | [6 empty] | Week 8 ¦ 21 Sep – 27 Sep | [6 empty] | Week 9 ¦ 28 Sep – 04 Oct | [6 empty] | Week 10 ¦ 05 Oct – 11 Oct | [6 empty] | Week 11 ¦ 12 Oct – 18 Oct | [6 empty] | Week 12 ¦ 19 Oct – 25 Oct | [6 empty] | Week 13 ¦ 26 Oct – 01 Nov | [6 empty] | Week 14 ¦ 02 Nov – 08 Nov | [6 empty] | Week 15 ¦ 09 Nov – 15 Nov | [6 empty] | Week 16 ¦ 16 Nov – 22 Nov | [6 empty] | Week 17 ¦ 23 Nov – 29 Nov | [6 empty] | Week 18 ¦ 30 Nov – 01 Dec
 | time axis 2026-08-03 to 2026-12-01
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2026-08-03 to 2026-12-01
Phase 1 — Project Initiation & Idea
Problem identification and project idea | Project Team | 100% | 2026-08-03 | 2026-08-05 | 3 | bar: 2026-08-03 to 2026-08-05
Motivation, objectives and scope definition | Project Team | 100% | 2026-08-04 | 2026-08-07 | 4 | bar: 2026-08-04 to 2026-08-07
Basic architecture and workflow planning | Project Team | 100% | 2026-08-06 | 2026-08-09 | 4 | bar: 2026-08-06 to 2026-08-09
Dataset/playbook decision and initial lab presentation | Project Team | 100% | 2026-08-08 | 2026-08-10 | 3 | bar: 2026-08-08 to 2026-08-10
Phase 2 — Project Proposal |  |  | 2019-01-06 | 2019-01-08 | 3
Proposal structure and content drafting | Project Team | 100% | 2026-08-11 | 2026-08-14 | 4 | bar: 2026-08-11 to 2026-08-14
Problem statement, methodology and deliverables | Project Team | 100% | 2026-08-12 | 2026-08-16 | 5 | bar: 2026-08-12 to 2026-08-16
Proposal finalization and submission | Project Team | 100% | 2026-08-16 | 2026-08-17 | 2 | bar: 2026-08-16 to 2026-08-17
Phase 3 — Requirements, Analysis & Design |  |  | 2019-01-15 | 2019-01-18 | 4
System requirements and module planning | Project Team | 100% | 2026-08-18 | 2026-08-23 | 6 | bar: 2026-08-18 to 2026-08-23
Initial prototype foundation and repository setup | Project Team | 100% | 2026-08-18 | 2026-08-30 | 13 | bar: 2026-08-18 to 2026-08-30
Use case and DFD design | Project Team | 100% | 2026-08-24 | 2026-08-31 | 8 | bar: 2026-08-24 to 2026-08-31
GitHub Pages / project documentation setup | Project Team | 100% | 2026-08-25 | 2026-08-31 | 7 | bar: 2026-08-25 to 2026-08-31
Phase 4 — Prototype Development |  |  | 2019-01-22 | 2019-01-26 | 5
Document ingestion, chunking and embeddings | Project Team | 100% | 2026-09-01 | 2026-09-05 | 5 | bar: 2026-09-01 to 2026-09-05
Clause retrieval and comparison pipeline | Project Team | 100% | 2026-09-03 | 2026-09-08 | 6 | bar: 2026-09-03 to 2026-09-08
Report generation and Streamlit interface | Project Team | 100% | 2026-09-06 | 2026-09-11 | 6 | bar: 2026-09-06 to 2026-09-11
Prototype integration and basic verification | Project Team | 100% | 2026-09-10 | 2026-09-13 | 4 | bar: 2026-09-10 to 2026-09-12
ER and Activity diagrams + presentation preparation | Project Team | 90% | 2026-09-11 | 2026-09-14 | 4 | bar: 2026-09-11 to 2026-09-14
Phase 5 — Pipeline Validation & Bug Fixing |  |  | 2019-01-29 | 2019-02-02 | 5
Fix chunking and verify chunk offsets | Project Team | 0% | 2026-09-15 | 2026-09-20 | 6 | bar: 2026-09-15 to 2026-09-20
Calibrate retrieval threshold and query phrasing | Project Team | 0% | 2026-09-18 | 2026-09-24 | 7 | bar: 2026-09-18 to 2026-09-24
Verify dataset loading, retrieval signatures and ground truth | Project Team | 0% | 2026-09-21 | 2026-09-26 | 6 | bar: 2026-09-21 to 2026-09-26
Verify rule-based comparator and LLM comparison path | Project Team | 0% | 2026-09-24 | 2026-09-30 | 7 | bar: 2026-09-24 to 2026-09-30
Phase 6 — Evaluation & Performance Testing |  |  | 2019-02-05 | 2019-02-10 | 6
Retrieval hit-rate and score-distribution evaluation | Project Team | 0% | 2026-09-28 | 2026-10-04 | 7 | bar: 2026-09-28 to 2026-10-04
End-to-end evaluation on synthetic contracts | Project Team | 0% | 2026-10-01 | 2026-10-07 | 7 | bar: 2026-10-01 to 2026-10-07
Real-world PDF upload and parser testing | Project Team | 0% | 2026-10-04 | 2026-10-09 | 6 | bar: 2026-10-04 to 2026-10-09
Performance analysis and evaluation report | Project Team | 0% | 2026-10-07 | 2026-10-12 | 6 | bar: 2026-10-07 to 2026-10-12
Phase 7 — System Integration & Documentation
Improve Streamlit workflow and user-facing output | Project Team | 0% | 2026-10-08 | 2026-10-17 | 10 | bar: 2026-10-08 to 2026-10-17
PDF/CSV report generation and output validation | Project Team | 0% | 2026-10-13 | 2026-10-20 | 8 | bar: 2026-10-13 to 2026-10-20
SRS, architecture and detailed design documentation | Project Team | 0% | 2026-10-15 | 2026-10-27 | 13 | bar: 2026-10-15 to 2026-10-27
Testing documentation, screenshots and project website updates | Project Team | 0% | 2026-10-22 | 2026-10-31 | 10 | bar: 2026-10-22 to 2026-10-31
Phase 8 — Final Testing & Stabilization
Clean-environment installation and dependency testing | Project Team | 0% | 2026-11-01 | 2026-11-05 | 5 | bar: 2026-11-01 to 2026-11-05
Unit, integration and regression testing | Project Team | 0% | 2026-11-04 | 2026-11-12 | 9 | bar: 2026-11-04 to 2026-11-12
Bug fixing, edge-case testing and UI polish | Project Team | 0% | 2026-11-10 | 2026-11-18 | 9 | bar: 2026-11-10 to 2026-11-18
Final prototype freeze and release candidate | Project Team | 0% | 2026-11-17 | 2026-11-20 | 4 | bar: 2026-11-17 to 2026-11-20
Phase 9 — Final Report, Demo & Submission
Final technical report and evaluation results | Project Team | 0% | 2026-11-18 | 2026-11-24 | 7 | bar: 2026-11-18 to 2026-11-24
Final presentation and demo preparation | Project Team | 0% | 2026-11-22 | 2026-11-27 | 6 | bar: 2026-11-22 to 2026-11-27
Final documentation review and corrections | Project Team | 0% | 2026-11-26 | 2026-11-30 | 5 | bar: 2026-11-26 to 2026-11-30
Final demo / submission / project closure | Project Team | 0% | 2026-12-01 | 2026-12-01 | 1 | bar: 2026-12-01
Insert new rows ABOVE this one
Legend: | Completed | Planned | Today | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
Customized for the Contract Playbook Comparison System project.
Timeline: 03-Aug-2026 to 01-Dec-2026.
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.